## Tabelle1
Date, Time | Length (min) | Task | Activity | Result | Responsibility | Remarks
2021-04-27 | 40 | First meeting | Decision on topic (from M1), Creation of Work Protocol, Discussion of used technologies | Work Protocol and git repository created Project: “Zum Anbeißen” RDBMS: MySQL NoSQL DB: MongoDB Webframework: Vue.js | Haider, Röck | Next meeting is planned in about two weeks
2021-04-27 | 80 | Creation of database schema | Implementation of the sql script for creating the database relations | Sql script for creation of database relations | Haider | Script will be checked by Röck
2021-05-01 | 65 | Check database schema | Rework of implementation of the sql script |  | Röck
2021-05-12 | 180 | Create empty vue app | Working on ui implementation of the app | Vue app with router and different views created. No functionality yet implemented. | Haider | Docker configuration should be created soon.
2021-05-12 | 70 | Create REST server | Research ways of connecting vue app with mysql database, test rest api with first sql query | Rest API created with express.js | Haider
2021-05-13 | 50 | Meeting | Discussion of done work Discussion of work to be done | Röck: Add Recipe + Properties Report Haider: Add Ingredient + Recipe/Meal Plan Report | Haider, Röck
2021-05-14 | 40 | Rework database schema | Reworked Constraints and Functions from Oracle->MySQL | Working SQL Script | Röck | varchar2 is only Oracle, we must stick to varchar
2021-05-17 | 480 | Added DB Filling Script | Script to fill random Data into the DB | Endpoints to fill random Data to DB | Röck
2021-05-21 | 100 | Create report 1, Implement Log in functionality | Working on first report. Creating view for displaying entries. | Table for mealplan/recipe report was created. Log in on home page implemented. | Haider | Api request for mealplans does not return data correctly.
2021-05-22 | 220 | Implement add recipe form | Fix bugs concerning report, implement APIs and UI for recipe use case | Input form for recipes added, improved report and fixed bugs | Haider | Ingredients can not be added for now
2021-05-22 | 110 | Improved UI, implemented use case | Add styles and nav bar to ui, fully implement recipe use case | UI is now tidier, has a nav bar for navigation, report 1 and use case 2 are implemented now. | Haider
2021-05-24 | 180 | Implement add Ingredient | Implemented the form and api for adding a custom Ingredient | Form and API Endpoint | Röck
2021-05-24 | 60 | Create Property Report | Implement Property Endpoint and frontend representation | Property Report | Röck
2021-05-25 | 60 | Meeting | discussed current implementation | Fixed compatibility issue windows - linux | Haider, Röck | Haider tries to get Docker to run Röck creates MongoDB ER-Diagram with VP
2021-05-27 | 150 | Fix docker configuration | Work on docker-compose and nginx configuration | Application and api are now accessible when running in multiple containers. Https using self-signed certificates was implemented. | Haider | The database access is not working currently. This issue should be fixed soon.
2021-05-27 | 180 | Try fixing docker configuration | Try fixing docker configuration. Fixed database access configuration | DB access fixed | Röck
2021-05-28 | 180 | ERD and Design Decisions | Created Mongo DB ER Design and write the Design Decisions | ERD, Design Decisions, Final Report Template | Röck | Need to get verified by Haider
2021-05-31 | 30 | Read report template with the mongoDB schema description | Read report, rewrite one section. Get to know the used schema for the mongoDB implementation. | Haider verified parts written by Röck. All looks great. | Haider
2021-06-04 | 120 | Work on migration process | Create endpoints for the migration process, start implementation of migration class | All necessary classes have been created, migration can be started from the frontend, migration of the ingredients table was successfully implemented | Haider | Migration step can be verified by switching from mysql to mongo and calling localhost:8000/api/mongo/ingredients in the browser, Real migration according to mongoDB scheme is still not implemented
2021-06-05 | 80 | Work on migration process | Try to migrate recipe with joined table | Recipe is joined with PreparationStep and migrated to mongo | Haider | The resulting json is not correct yet.
2021-06-12 | 150 | Implemented recipe meal plans report with migrated data | Recreate sql statement with new mongo db schema | Report can now be accessed via fronted using mysql and mongodb | Haider | The report is not correct. The filtering could not be achieved yet.
2021-06-14 | 120 | Added Ingredients to Recipe Migration |  |  | Röck
2021-06-14 | 20 | Meeting | Discuss last steps for submission | Both members will finish the migrated data and corresponding reports. | Haider, Röck | Last meeting will be scheduled for Tuesday (submission)
2021-06-14 | 120 | Finish report using mongo and use case | Refine report (add filter and sort), implement add recipe in mongo | Report and use case can now be used with mongo db. | Haider
2021-06-15 | 90 | Work on submission paper | Fix last bugs about the mongo report and use case, work on report | Report and use case work again with updated schema. Mongo/SQL queries were added to the submission document. | Haider
2021-06-15 | 240 | Migration | Added other Migrations from SQL to MongoDB | All collections are getting created autoamticall with the specified schema | Röck
2021-06-15 | 90 | Add Ingredients | Implemented adding ingredients to MongoDB | Ingredients can now be added to the MongoDB | Röck
2021-06-15 | 30 | Properties Report | Started MongoDB Properties Report | Not finished Properties Report | Röck
2021-06-16 | 120 | Properties Report | Finished Properties Report in MongoDB | Full working Properties Report, giving same values as SQL Report | Röck
2021-06-17 | 60 | Properties Report | Improved Report performance |  | Röck